## Sheet1
Cesium Port Status
Module | Status | Swift port | Tests | Notes
Core
ArcGisImageServerTerrainProvider.js | Not started | Not started | Not started
AssociativeArray.js | Not started | Not started | Not started
AxisAlignedBoundingBox.js | Not started | Not started | Not started
BingMapsApi.js | Not started | Not started | Not started
BoundingRectangle.js | Complete | Not started | Not started
BoundingSphere.js | Partial | Partial | Not started
BoxGeometry.js | Not started | Not started | Not started
BoxOutlineGeometry.js | Not started | Not started | Not started
Cartesian2.js | Complete | Not started | Not started
Cartesian3.js |  | Complete | Not started | Revert to struct and replace forced packedlength once compiler support
Cartesian4.js | Complete | Partial | Not started
Cartographic.js |  | Complete | Not started
CatmullRomSpline.js | Not started | Not started | Not started
CesiumTerrainProvider.js | Not started | Not started | Not started
CircleGeometry.js | Not started | Not started | Not started
CircleOutlineGeometry.js | Not started | Not started | Not started
Clock.js | Not started | Not started | Not started
ClockRange.js | Not started | Not started | Not started
ClockStep.js | Not started | Not started | Not started
Color.js | Not started | Not started | Not started
ColorGeometryInstanceAttribute.js | Not started | Not started | Not started
ComponentDatatype.js | Not started | Not started | Not started
Core.profile.js | Not started | Not started | Not started
CornerType.js | Not started | Not started | Not started
CorridorGeometry.js | Not started | Not started | Not started
CorridorGeometryLibrary.js | Not started | Not started | Not started
CorridorOutlineGeometry.js | Not started | Not started | Not started
Credit.js | Not started | Not started | Not started
CubicRealPolynomial.js | Not started | Not started | Not started
CylinderGeometry.js | Not started | Not started | Not started
CylinderGeometryLibrary.js | Not started | Not started | Not started
CylinderOutlineGeometry.js | Not started | Not started | Not started
DefaultProxy.js | Not started | Not started | Not started
DeveloperError.js | Not started | Not started | Not started
EarthOrientationParameters.js | Not started | Not started | Not started
EarthOrientationParametersSample.js | Not started | Not started | Not started
EllipseGeometry.js | Not started | Not started | Not started
EllipseGeometryLibrary.js | Not started | Not started | Not started
EllipseOutlineGeometry.js | Not started | Not started | Not started
Ellipsoid.js |  | Complete | Not started
EllipsoidGeodesic.js | Not started | Not started | Not started
EllipsoidGeometry.js | Partial | Not started | Not started
EllipsoidOutlineGeometry.js | Not started | Not started | Not started
EllipsoidTangentPlane.js | Not started | Not started | Not started
EllipsoidTerrainProvider.js | Partial | Not started | Not started
EllipsoidalOccluder.js |  | Partial | Not started | Missing array return bug
EncodedCartesian3.js | Not started | Not started | Not started
Event.js | Not started | Not started | Not started
EventHelper.js | Not started | Not started | Not started
FAR.js | Not started | Not started | Not started
FeatureDetection.js | Not started | Not started | Not started
Fullscreen.js | Not started | Not started | Not started
GeographicProjection.js | Complete | Not started | Not started
GeographicTilingScheme.js | Complete | Not started | Not started
Geometry.js | Not started | Not started | Not started
GeometryAttribute.js | Not started | Not started | Not started
GeometryAttributes.js | Not started | Not started | Not started
GeometryInstance.js | Not started | Not started | Not started
GeometryInstanceAttribute.js | Not started | Not started | Not started
GeometryPipeline.js | Not started | Not started | Not started
HeightmapTerrainData.js | Partial | Not started | Not started
HeightmapTessellator.js | Partial | Not started | Not started
HermitePolynomialApproximation.js | Not started | Not started | Not started
HermiteSpline.js | Not started | Not started | Not started
Iau2000Orientation.js | Not started | Not started | Not started
Iau2006XysData.js | Not started | Not started | Not started
Iau2006XysSample.js | Not started | Not started | Not started
IauOrientationAxes.js | Not started | Not started | Not started
IauOrientationParameters.js | Not started | Not started | Not started
IndexDatatype.js | Partial | Not started | Not started
InterpolationAlgorithm.js | Not started | Not started | Not started
Intersect.js |  | Complete | Not started
IntersectionTests.js | Not started | Not started | Not started
Intersections2D.js | Not started | Not started | Not started
Interval.js |  | Complete | Not started
Iso8601.js | Not started | Not started | Not started
JulianDate.js | Not porting | Not started | Not started
KeyboardEventModifier.js | Not started | Not started | Not started
LagrangePolynomialApproximation.js | Not started | Not started | Not started
LeapSecond.js | Not started | Not started | Not started
LinearApproximation.js | Not started | Not started | Not started
LinearSpline.js | Not started | Not started | Not started
Math.js | Partial | Not started | Not started
Matrix2.js | Not started | Not started | Not started
Matrix3.js | Not started | Not started | Not started
Matrix4.js | Partial | Not started | Not started | Interface only
NearFarScalar.js | Not started | Not started | Not started
ObjectOrientedBoundingBox.js | Not started | Not started | Not started
Occluder.js | Not started | Not started | Not started
Packable.js | Not started | Not started | Not started
PackableForInterpolation.js | Not started | Not started | Not started
PixelFormat.js | Not started | Not started | Not started
Plane.js | Not started | Not started | Not started
PolygonGeometry.js | Not started | Not started | Not started
PolygonGeometryLibrary.js | Not started | Not started | Not started
PolygonOutlineGeometry.js | Not started | Not started | Not started
PolygonPipeline.js | Not started | Not started | Not started
PolylineGeometry.js | Not started | Not started | Not started
PolylinePipeline.js | Not started | Not started | Not started
PolylineVolumeGeometry.js | Not started | Not started | Not started
PolylineVolumeGeometryLibrary.js | Not started | Not started | Not started
PolylineVolumeOutlineGeometry.js | Not started | Not started | Not started
PrimitiveType.js | Not started | Not started | Not started
QuadraticRealPolynomial.js | Not started | Not started | Not started
QuantizedMeshTerrainData.js | Not started | Not started | Not started
QuarticRealPolynomial.js | Not started | Not started | Not started
Quaternion.js | Partial | Not started | Not started | Depends on Matrix3
QuaternionSpline.js | Not started | Not started | Not started
Queue.js | Not started | Not started | Not started
Ray.js | Complete | Not started | Not started
Rectangle.js |  | Complete | Not started
RectangleGeometry.js | Not started | Not started | Not started
RectangleOutlineGeometry.js | Not started | Not started | Not started
ReferenceFrame.js | Not started | Not started | Not started
RequestErrorEvent.js | Not started | Not started | Not started
RuntimeError.js | Not started | Not started | Not started
ScreenSpaceEventHandler.js | Not started | Not started | Not started
ScreenSpaceEventType.js | Not started | Not started | Not started
ShowGeometryInstanceAttribute.js | Not started | Not started | Not started
Simon1994PlanetaryPositions.js | Not started | Not started | Not started
SimplePolylineGeometry.js | Not started | Not started | Not started
SphereGeometry.js | Not started | Not started | Not started
SphereOutlineGeometry.js | Not started | Not started | Not started
Spherical.js | Complete | Partial | Not started
Spline.js | Not started | Not started | Not started
TaskProcessor.js | Not started | Not started | Not started
TerrainData.js | Complete | Not started | Not started
TerrainMesh.js | Complete | Not started | Not started
TerrainProvider.js | Complete | Not started | Not started
TileProviderError.js | Not started | Not started | Not started
TilingScheme.js | Complete | Not started | Not started
TimeConstants.js | Not started | Not started | Not started
TimeInterval.js | Not started | Not started | Not started
TimeIntervalCollection.js | Not started | Not started | Not started
TimeStandard.js | Not started | Not started | Not started
Tipsify.js | Not started | Not started | Not started
Transforms.js | Not started | Not started | Not started
TridiagonalSystemSolver.js | Not started | Not started | Not started
VRTheWorldTerrainProvider.js | Not started | Not started | Not started
VertexFormat.js | Complete | Not started | Not started
Visibility.js | Not started | Not started | Not started
WallGeometry.js | Not started | Not started | Not started
WallGeometryLibrary.js | Not started | Not started | Not started
WallOutlineGeometry.js | Not started | Not started | Not started
WebMercatorProjection.js | Complete | Not started | Not started
WebMercatorTilingScheme.js | Complete | Not started | Not started
WindingOrder.js | Not started | Not started | Not started
barycentricCoordinates.js | Not started | Not started | Not started
binarySearch.js | Not started | Not started | Not started
buildModuleUrl.js | Not started | Not started | Not started
cancelAnimationFrame.js | Not started | Not started | Not started
clone.js | Not porting | Not started | Not started | NSCopying
combine.js | Not porting | Not started | Not started | NSArray
createGuid.js | Not porting | Not started | Not started | NSUUID
defaultValue.js |  | Complete | Not started
defineProperties.js | Not started | Not started | Not started
defined.js | Not started | Not started | Not started
deprecationWarning.js | Not started | Not started | Not started
destroyObject.js | Not started | Not started | Not started
formatError.js | Not started | Not started | Not started
freezeObject.js | Not porting | Not started | Not started | readonly
getFilenameFromUri.js | Not started | Not started | Not started
getImagePixels.js | Not started | Not started | Not started
getTimestamp.js | Not started | Not started | Not started
isArray.js | Not started | Not started | Not started
isCrossOriginUrl.js | Not started | Not started | Not started
isLeapYear.js | Not started | Not started | Not started
jsonp.js | Not started | Not started | Not started
loadArrayBuffer.js | Not started | Not started | Not started
loadBlob.js | Not started | Not started | Not started
loadImage.js | Not started | Not started | Not started
loadImageViaBlob.js | Not started | Not started | Not started
loadJson.js | Not started | Not started | Not started
loadText.js | Not started | Not started | Not started
loadWithXhr.js | Not started | Not started | Not started
loadXML.js | Not started | Not started | Not started
mergeSort.js | Not started | Not started | Not started
parseResponseHeaders.js | Not started | Not started | Not started
pointInsideTriangle.js | Not started | Not started | Not started
requestAnimationFrame.js | Not started | Not started | Not started
sampleTerrain.js | Not started | Not started | Not started
subdivideArray.js | Not started | Not started | Not started
throttleRequestByServer.js | Not started | Not started | Not started
wrapFunction.js | Not started | Not started | Not started
writeTextToCanvas.js | Not started | Not started | Not started
Renderer
AutomaticUniforms.js | Not started | Not started | Not started
Buffer.js | Not started | Not started | Not started
BufferUsage.js | Not started | Not started | Not started
ClearCommand.js | Not started | Not started | Not started
Context.js | Partial | Not started | Not started
CubeMap.js | Not started | Not started | Not started
CubeMapFace.js | Not started | Not started | Not started
DrawCommand.js | Partial | Not started | Not started | Init only
Framebuffer.js | Not started | Not started | Not started
MipmapHint.js | Not started | Not started | Not started
PassState.js | Partial | Not started | Not started | interface only
PickFramebuffer.js | Not started | Not started | Not started
PixelDatatype.js | Not started | Not started | Not started
RenderState.js | Partial | Not started | Not started | Interface only
Renderbuffer.js | Not started | Not started | Not started
RenderbufferFormat.js | Not started | Not started | Not started
Renderer.profile.js | Not started | Not started | Not started
ShaderCache.js | Not started | Not started | Not started
ShaderProgram.js | Not started | Not started | Not started
Texture.js | Not started | Not started | Not started
TextureMagnificationFilter.js | Not started | Not started | Not started
TextureMinificationFilter.js | Not started | Not started | Not started
TextureWrap.js | Not started | Not started | Not started
UniformState.js | Not started | Not started | Not started | interface only
VertexArray.js | Not started | Not started | Not started
VertexArrayFacade.js | Not started | Not started | Not started
createShaderSource.js | Not started | Not started | Not started
loadCubeMap.js | Not started | Not started | Not started
Scene
AnimationCollection.js | Not started | Not started | Not started
Appearance.js | Not started | Not started | Not started
ArcGisMapServerImageryProvider.js | Not started | Not started | Not started
Billboard.js | Not started | Not started | Not started
BillboardCollection.js | Not started | Not started | Not started
BingMapsImageryProvider.js | Not started | Not started | Not started
BingMapsStyle.js | Not started | Not started | Not started
BlendEquation.js | Not started | Not started | Not started
BlendFunction.js | Not started | Not started | Not started
BlendingState.js | Not started | Not started | Not started
Camera.js | Partial | Not started | Not started
CameraEventAggregator.js | Not started | Not started | Not started
CameraEventType.js | Not started | Not started | Not started
CameraFlightPath.js | Not started | Not started | Not started
CreditDisplay.js | Not started | Not started | Not started
CullFace.js | Not started | Not started | Not started
CullingVolume.js | Not started | Not started | Not started
CustomSensorVolume.js | Not started | Not started | Not started
DebugAppearance.js | Not started | Not started | Not started
DebugModelMatrixPrimitive.js | Not started | Not started | Not started
DepthFunction.js | Not started | Not started | Not started
DiscardMissingTileImagePolicy.js | Not started | Not started | Not started
EllipsoidPrimitive.js | Not started | Not started | Not started
EllipsoidSurfaceAppearance.js | Not started | Not started | Not started
FXAA.js | Not started | Not started | Not started
FrameState.js | Complete | Not started | Not started
FrustumCommands.js | Not started | Not started | Not started
Globe.js | Partial | Not started | Not started
GlobeSurface.js | Not started | Not started | Not started
GlobeSurfaceShaderSet.js | Not started | Not started | Not started
GoogleEarthImageryProvider.js | Not started | Not started | Not started
GridImageryProvider.js | Not started | Not started | Not started
HorizontalOrigin.js | Not started | Not started | Not started
Imagery.js | Not started | Not started | Not started
ImageryLayer.js | Not started | Not started | Not started
ImageryLayerCollection.js | Not started | Not started | Not started
ImageryProvider.js | Not started | Not started | Not started
ImageryState.js | Not started | Not started | Not started
Label.js | Not started | Not started | Not started
LabelCollection.js | Not started | Not started | Not started
LabelStyle.js | Not started | Not started | Not started
Material.js | Not started | Not started | Not started
MaterialAppearance.js | Not started | Not started | Not started
Model.js | Not started | Not started | Not started
ModelAnimation.js | Not started | Not started | Not started
ModelAnimationCache.js | Not started | Not started | Not started
ModelAnimationCollection.js | Not started | Not started | Not started
ModelAnimationLoop.js | Not started | Not started | Not started
ModelAnimationState.js | Not started | Not started | Not started
ModelMaterial.js | Not started | Not started | Not started
ModelMesh.js | Not started | Not started | Not started
ModelNode.js | Not started | Not started | Not started
ModelTypes.js | Not started | Not started | Not started
Moon.js | Not started | Not started | Not started
NeverTileDiscardPolicy.js | Not started | Not started | Not started
OIT.js | Not started | Not started | Not started
OpenStreetMapImageryProvider.js | Not started | Not started | Not started
OrthographicFrustum.js | Not started | Not started | Not started
Pass.js | Not started | Not started | Not started
PerInstanceColorAppearance.js | Not started | Not started | Not started
PerformanceDisplay.js | Not started | Not started | Not started
PerspectiveFrustum.js | Partial | Not started | Not started
PerspectiveOffCenterFrustum.js | Not started | Not started | Not started
Polygon.js | Not started | Not started | Not started
Polyline.js | Not started | Not started | Not started
PolylineCollection.js | Not started | Not started | Not started
PolylineColorAppearance.js | Not started | Not started | Not started
PolylineMaterialAppearance.js | Not started | Not started | Not started
Primitive.js | Partial | Not started | Not started
PrimitiveCollection.js | Not started | Not started | Not started
PrimitivePipeline.js | Not started | Not started | Not started
PrimitiveState.js | Not started | Not started | Not started
RectanglePrimitive.js | Not started | Not started | Not started
RectangularPyramidSensorVolume.js | Not started | Not started | Not started
Scene.js | Partial | Not started | Not started
Scene.profile.js | Not started | Not started | Not started
SceneMode.js | Not started | Not started | Not started
SceneTransforms.js | Not started | Not started | Not started
SceneTransitioner.js | Not started | Not started | Not started
ScreenSpaceCameraController.js | Not started | Not started | Not started
SensorVolumeCollection.js | Not started | Not started | Not started
SingleTileImageryProvider.js | Not started | Not started | Not started
SkyAtmosphere.js | Not started | Not started | Not started
SkyBox.js | Not started | Not started | Not started
StencilFunction.js | Not started | Not started | Not started
StencilOperation.js | Not started | Not started | Not started
Sun.js | Not started | Not started | Not started
SunPostProcess.js | Not started | Not started | Not started
TerrainState.js | Not started | Not started | Not started
TextureAtlas.js | Not started | Not started | Not started
TextureAtlasBuilder.js | Not started | Not started | Not started
Tile.js | Not started | Not started | Not started
TileCoordinatesImageryProvider.js | Not started | Not started | Not started
TileDiscardPolicy.js | Not started | Not started | Not started
TileImagery.js | Not started | Not started | Not started
TileMapServiceImageryProvider.js | Not started | Not started | Not started
TileReplacementQueue.js | Not started | Not started | Not started
TileState.js | Not started | Not started | Not started
TileTerrain.js | Not started | Not started | Not started
VerticalOrigin.js | Not started | Not started | Not started
ViewportQuad.js | Not started | Not started | Not started
WebMapServiceImageryProvider.js | Not started | Not started | Not started
createTangentSpaceDebugPrimitive.js | Not started | Not started | Not started
terrainAttributeLocations.js | Not started | Not started | Not started
DynamicScene